## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/3 -9/10 | Created user stories, defined roles, determined tools, created high level design, created mock ui, defined project file structure installed required software, work on Lab1 | Pivotal Tacker does not sych to github | Facilatators joined late causing the team to hold off on creating users stories, finalizing our design, and creating our requirements which put us behind schedule. | Teams has decided to meet tuesday an hour before class to try to catch up | 5 | 5 | 4 | 4 | 5 | 40+ | 10 | 6 | 22 | 5 | 16 | 0 | 0 | 6 | 32 | 8
1
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Joshua Shilts | Iteration 0: 1. Filled in and drafted SPPP document |  |  |  | Iteration 0: 1. Created presentation | Iteration 0: 1. Completed Lab1 |  | Iteration 0: 1. Assisted in setting up branch protections for main | Iteration 0: 1. Led team discussion in meetinfs 2. Assisted in git configuration 3. Assisted in python configuration 4. Assisted in IDE configuration 5. General Design discussion questions
Elizabeth Tyree | Iteration 0: 1. Added API name, Kaggle Dataset reference, and contributed to Functional Requirements. 2. Reviewed SPPP document and made mior edits | Iteration 0: Created Pivotal tracker board and initial Epic and planning story. |  |  |  | Iteration 0: 1. Completed Lab1 |  |  | Iteration 0: 1. Reviewed all 3 Kaggle datasets of interest. Determined that 1 dataset is a subset of another. 2. Reviewed SPPP document and made mior edits 3. Reviewed Database Requirements, made minor edits and added that we a going to use the IMDB Top 250 dataset from Kaggle. 4. Named the API 5. Reviewed README.md and added API Name. 6. Created Team 6 Pivitol Tracker board.
Ricky Zheng | Iteration 0: 1. Reviewed and verified configuration management plan and other sections on SPPP. | [6 empty] | Iteration 0: 1. Set up multiple branches for different tasks. 2. Wrote initial README.md template. 3. Created a how-to document detailing the git commit process for Lab1 and in general. 4. Uploaded data sets for future use and examples. 5. Reviewed and merged Lab1 pull request. 6. Deleted Lab1 branch after PR was approved by multiple team members. | Iteration 0: 1. Discussed and finalized team meeting times and dates. 2. Discussed and finalized team leader assignments. 3. Recorded and wrote Sep. 7 section of meeting minutes document.
Alex Flinchum | Iteration 0: 1. Reviewed and verified Quality Assurance Plan and other sections on SPPP.
James Zheng | Iteration 0: 1. Assisted on the selection of dataset and the look of the UI | [6 empty] | Iteration 0: 1. created the ruleset on github, require 3 team members in order to pull | Iteration 0: 1. recorded the Sep. 10 section (meeting 3) of the meeting minutes document.
Rekik Mengstu | Iteration 0: 1. Tracked project requirements and steps using pivotal track

## Joshua Shilts
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
0 | 09/03-09/10 | 2024-10-15 | 9 | 6 | 0 - read a tutorial on React and watched several youtube videos on it 0- Assisted team member in getting the dev enviroments set up 2 - Worked with team on high evel design and UI design. 5 - Created User stories 6 - Assisted team with git and got git setup 7. Prepared presentation and other documentation | 3 | 0 | 2 | 0 | 0 | 1 | 5 | 4 | 1. Drafted SPPP 2. Set-up and configured Git, Podman, Python, Pip, Flask, Github, NodeJs, 3. Created High level design documentation 4. Created and presented presentation | 1. All team mebers using different OS's making set-up and configuration a large and painful task 2. There was not a facilatator for almost the entire iteration which caused a bottleneck in our ability to fill in requirements and determine if our project design was in scope. | 1. Met with team members and work for about 3-4 hours to resolve all issues with devices and tools. 2. Plan to mitgate absence of facilitaor is to delegate and to swarm on the requirements while several team members develop the skeleton of the appication. | 1. Continue to define Requirements 3. Implement a basic skeleton microservice application | 15

## Liz Tyree
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
0 | 09/03-09/10 | 2024-10-15 | 9 | 6 | 0 - read a tutorial on React and watched several youtube videos on it 0- Assisted team member in getting the dev enviroments set up 2 - Worked with team on high evel design and UI design. 5 - Created User stories 6 - Assisted team with git and got git setup 7. Prepared presentation and other documentation | 3 | 0 | 3 | 0 | 0 | 1 | 5 | 4 | 1. Drafted SPPP 2. Set-up and configured Git, Podman, Python, Pip, Flask, Github, NodeJs, 3. Created High level design documentation 4. Created and presented presentation | 1. All team mebers using different OS's making set-up and configuration a large and painful task 2. There was not a facilatator for almost the entire iteration which caused a bottleneck in our ability to fill in requirements and determine if our project design was in scope. | 1. Met with team members and work for about 3-4 hours to resolve all issues with devices and tools. 2. Plan to mitgate absence of facilitaor is to delegate and to swarm on the requirements while several team members develop the skeleton of the appication. | 1. Continue to define Requirements 3. Implement a basic skeleton microservice application | 16

## James Zheng
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
0 | 09/03-09/10 | 12 | 6 | 6 | 0 - how to operate and set up github as well as ssh key 2 - asisted on high level deisgn for the UI and dataset 6- setup github and git as well as all the other programs needed to complete project | 4 | 0 | 2 | 0 | 0 | 0 | 6 | 0 | 1. filled out Meeting 3 of the meeting minutes 2. set up git, github, python, Flask, NodeJs, docker, pivotaltracker | 1. had issue setting up ssh on git 2. Missing facilitator to answer questions and feedbacks to advance with tasks 3. installing docker and getting it setup properly | 1. ssh has been successfully setup 2. we were assigned a facilitator and he was able to answer all of our unanswered questions 3. asking teamates for help and doing our research to resolve the problem | 1. Continue to define Requirements 2. finalize the high level UI design 3. implement a basic skeleton for the program 5. continuing to communicate with team memebrs to complete task on pivotal tracker | 12

## Rekik Mengstu
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 6 | 5 | 1 | 0 - learn git and django, read several tutorials 6 - set up git 7 - research | 2 |  |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 8
0 | 09/03-09/10 | 2024-10-15 | 7 | 5 | 0 - watched several youtube videos on it 5 - Created User stories 6 - got help from team mates setting up git 7. worked on pivotal track | 3 | 0 | 0 | 0 | 0 | 1 | 5 | 4 | 2. Set-up and configured Git, Podman, Python, Pip, Flask, Github, NodeJs, | 1. different OS's making set-up and configuration complicated 2. There was not a facilatator 3. Being the newest member of the team with the least experience made me doubt myself | 1. Met with team members and work for about 3-4 hours per meeting | 1. Continue to define Requirements 3. Implement a basic skeleton microservice application | 15

## Ricky Zheng
Your Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03-09/10 | 18 | 12 | 6 | 0 - learned about git, how to setup multiple technologies (Docker, Python, PIP, nodeJS, SQLite), and learned about Pivotal Tracker. 2- Work together with team developing and brainstorming high level design of project application. 5 - Established and finalized correct channels of team communication. Also, finalized teammeeting dates and times. 6 - Created multiple branches for designated work such as Lab1, adding data sets, adding documention, and updating README.md. Created documentation for team members regarding git commit process. Also, managed pull request as both a assignee, reviewer, and configuration leader. Merged Lab1 pull request and deleted Lab1 branch. | 5 | 0 | 4 | 0 | 0 | 2 | 7 | N/A | 1. Modified and reviewed configuration management section and other sections of SPPP. 2. Set up multiple git branches for different purposes such as Lab1 and adding data sets. Modified README.md in team project repository. 3. Created how-to documentation explaining the process of committing files in Git and GitHub. 4. Wrote 9/5 meeting minutes report. | 1. Initial unfamiliarity with git process when working with other team members. 2. Unfamiliarity working with new tech stack (Docker, Python Flask, etc.) 3. Unsure of final facilitator for our team. 4. Confusion and misunderstanding of necessary documents required for group and individual submission. | 1. Issue has been mostly resolved. Git will be a ongoing learning experience for the team and myself. 2. As development and implementation tasks start to ramp up next week, expect this issue to slowly resolve as the development of the application progresses. 3. Issue resolved. Final facilitator has been assigned to our team. 4. Similiar to issue 2, issue should slowly resolve as team and individual document submission occur this week and the following weeks. | 1 - Continue to learn about project tech stack. 2 - Work on and complete Lab2. 3 - Research and investigate level of effort in implementing Python Flask application with GitHub pipeline. 4 - Manage GitHub project repository. Create, pull request, review, and merge appropriate branches depending on tasks. 5 - Assist and update team members regarding any changes to the team project GitHub repository. | 20

## Alex Flinchum
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 7 | 6 | 1 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 3 | 1 |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 6
0 | 09/03-09/10 | 16 | 10 | 6 | 0 - Learing to set up and exicute the teachnology we will be using 1 - Worked on Database requirments and other documentation 2 - Worked with team in creating our projects focus 5 - Discused team meeting times and channels of communication, alone with the practice of tracking tasks 6 - Assisted team with git and got git setup; Established a new branch and created files for that branch | 4 | 5 | 2 | 0 | 0 | 1 | 4 | N/A | 1. Discussed the QA requirments in the team meetins and reviewd teh details established in the SPPP 2. Set up git on my machine and created the Lab1 from teh main branch along with the team.md file 3. Working on documenting the database requirments in an offical documentation | 1. Having issues with getting pip and flask installed 2. Need to advance my knowledge of working with docker and running it 3. Confusion on the location of documentation and how to go about implimenting it | 1. Will set about time to go ver pip and flask instilation as well as knowledge on docker, This can be during a team meeting where we set asside time to run through these areas 2. Issue Resolved: the location of our teams documentation has been established and have been able to run through it | 1. Continue to learn the procjects tech, specifically docker and flask 2. Complete database requirment documentation 3. Research pipline cpabilities for a python project | 20