## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
This sheet should be completed by the team leader (or other member in the team) by the end of each iteration.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Any other metrics defined in your SPPP
0 | 9/3 -9/10 | Created user stories, defined roles, determined tools, created high level design, created mock ui, defined project file structure installed required software, work on Lab1 | Pivotal Tacker does not sych to github | Facilatators joined late causing the team to hold off on creating users stories, finalizing our design, and creating our requirements which put us behind schedule. | Teams has decided to meet tuesday an hour before class to try to catch up | 5 | 5 | 4 | 4 | 5 | 40+ | 10 | 6 | 22 | 5 | 16 | 0 | 0 | 6 | 32 | 8
1 | 9/11 -9/22 | Creted more user stories Created design and test design documentation Created database design documentation Created and delieved frontend MVP Created pipeline Started implementation of integration testing Started work on UI improvements Started implementating database | Issues running frontend docker container in pipeline Devlopment enviroment set-up issue or IDE Trouble with Docker compose running with Podman | 1. Team members moving on to other work before completeing previous task. 2. Some member not understanding what to do before starting work. 3. Was not entirly sure still how to write out requirements 4. Not clear on what the difference is between the two different video presentations. | Synch with facilatator to help with how to write out requirements and to clarify what is exactly expected in the video presentations | 3 | 1 | 2 | 13 | 2 | 60 | 40 | 15 | 29 | 6 | 16 | 4 | 27.5 | 15 | 11.5 | 14
2
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments
Joshua Shilts | Iteration 0: 1. Filled in and drafted SPPP document |  | Iteration 1: Created SDD | Iteration 1: Reviewed STD | Iteration 0: 1. Created presentation | Iteration 0: 1. Completed Lab1 Iteration 1: Completed Lab2 Created Backend MVP Created Frontend MVP |  | Iteration 0: 1. Assisted in setting up branch protections for main | Iteration 0: 1. Led team discussion in meetinfs 2. Assisted in git configuration 3. Assisted in python configuration 4. Assisted in IDE configuration 5. General Design discussion questions
Elizabeth Tyree | Iteration 0: 1. Added API name, Kaggle Dataset reference, and contributed to Functional Requirements. 2. Reviewed SPPP document and made mior edits Ieration 1: 1. Created user and deleopment stories in both pivital tracker and SPPP 2. Helped to refine Functional Requirements | Iteration 0: Created Pivotal tracker board and initial Epic and planning story. Iteration 1: Mostly worked on Database reated analysis and tasks on Pivotal Tracker. | Iteration 1: Had colaborative discussions about requirements and design with teammates. My teammates updated the SDD. | Iteration 1: My teammates handeled this. | Iteration 1: 1. Created presentation with James | Iteration 0: 1. Completed Lab1 | Iteration 1: Tested database creation. |  | Iteration 1: 1. Reviewed presenation, SPPP, piviotal tracker, and looked over a few pull requests on GitHub.
Ricky Zheng | Iteration 0: 1. Reviewed and verified configuration management plan and other sections on SPPP. |  |  | Iteration 1: 1. Added pipeline workflow details to Automated Testing Report section. |  | Iteration 1: 1. Implemented initial GitHub Actions pipeline workflow for project repository. | Iteration 1: 1. Tested and passed 3 seperate jobs (Docker-and-Python-Flask-Service, Node-Service, and Docker-and-Node Service) on GitHub Actions pipeline workflow. | Iteration 0: 1. Set up multiple branches for different tasks. 2. Wrote initial README.md template. 3. Created a how-to document detailing the git commit process for Lab1 and in general. 4. Uploaded data sets for future use and examples. 5. Reviewed and merged Lab1 pull request. 6. Deleted Lab1 branch after PR was approved by multiple team members. Iteration 1: 1. Designed a workflow structure in GitHub Actions for our project repository. 2. Implemented initial pipeline workflow where 3 jobs are ran after a commit occurs for every project branch. 3. Created dev branch and multiple other feature branches. 4. Deleted obsolete branches. 5. Created and reviewed mulitple pull requests. | Iteration 0: 1. Discussed and finalized team meeting times and dates. 2. Discussed and finalized team leader assignments. 3. Recorded and wrote Sep. 7 section of meeting minutes document. Iteration 1: 1. Recorded and wrote multiple meeting minutes reports. 2. Discussed design for GitHub Actions pipeline workflow structure.
Alex Flinchum | Iteration 0: 1. Reviewed and verified Quality Assurance Plan and other sections on SPPP. |  | Iteration 1: 1. Filled out Database Design with description of the projects design for SDD | Iteration 1: 1. Filled out Manual Testing Report and Testing Summary with the progess made this iteration and the test cases conducted this iteration. 2. Filled out Testing Summary with the how our test cases will be set up fro acceptance tests. 3. Filled out Testing Metrics with what teh expected results will follow for a test case. |  |  | Iteration 1: 1. Created two test cases for Create Frontend MVP and Create Backend MVP stories and proceded to test these two stories based off the test cases. | Iteration 1: 1. Merged the database documents into our dev branch | Iteration 1: 1. Discused database design with the team to finalize this portion of the project 2. Discussed the process of creating test cases. 3. Reviewed process of building and running project for dev work.
James Zheng | Iteration 0: 1. Assisted on the selection of dataset and the look of the UI Iteration 1: 1. filling in and assisted on the user stories |  |  |  | Iteration 1: 1. created and participated in presentation and video |  |  | Iteration 0: 1. created the ruleset on github, require 3 team members in order to pull iteration 1: 1. creating a branch for testing UI layout code 2. review and accepted pull requests | Iteration 0: 1. recorded the Sep. 10 section (meeting 3) of the meeting minutes document. Iteration 1: 1. back filling in for some missed information on the meeting minutes doc and recording 2. dispalying a draw up of the UI layout
Rekik Mengstu | Iteration 0: 1. Tracked project requirements and steps using pivotal track

## Joshua Shilts
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03-09/10 | 2024-10-15 | 9 | 6 | 0 - read a tutorial on React and watched several youtube videos on it 0- Assisted team member in getting the dev enviroments set up 2 - Worked with team on high evel design and UI design. 5 - Created User stories 6 - Assisted team with git and got git setup 7. Prepared presentation and other documentation | 4 | 2 | 3 | 3 | 2 | 2 | 1 | 0 |  | 1. Trying to run frontend docker container in pipeline was throwing error 2. Troubles configuring pycharm to use proper packages. 3. Issues using Docker compose with podman | 1. Did research on react and re-generated package-lock.json file and resolve issue in pipeline 2. Removed all packages and resinstalled packages and pycharm started woring correctly again. 3. Still troubling shooting issue realated to Podman and Docker-compose | 3. Continue with python implementation for database call 3 &4. Begin implementing and unti test and putting them into a pipeline. | 15
1 | 9/11 -9/22 | 20-30 | 24 | 16 | Synch with facilatator to help with how to write out requirements and to clarify what is exactly expected in the video presentations | 2 | 6 | 4 | 10 | 8 | 4 | 2 | 4 | Creted more user stories Created SDD Created MVP for frontend dockerized Updated Readme Updated SPPP Docker Compose training | Issues running frontend docker container in pipeline Devlopment enviroment set-up issue or IDE Trouble with Docker compose running with Podman | Resolved issue after doing research and regenerating a package-lock.json Retired issue by making sure everyone can run the code on their machine. Need to do some more reading on docker-compose still having issues with it | Continue with integration testing work Set-up database install scripts Integrate tests into pipeline Create calls from Python to database. Get Docker compose running | 40

## Liz Tyree
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Backup Project Leader, requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03-09/10 | 2024-10-15 | 9 | 6 | 0 - read a tutorial on React and watched several youtube videos on it 0- Assisted team member in getting the dev enviroments set up 2 - Worked with team on high evel design and UI design. 5 - Created User stories 6 - Assisted team with git and got git setup 7. Prepared presentation and other documentation | 3 | 0 | 3 | 0 | 0 | 1 | 5 | 4 | 1. Drafted SPPP 2. Set-up and configured Git, Podman, Python, Pip, Flask, Github, NodeJs, 3. Created High level design documentation 4. Created and presented presentation | 1. All team mebers using different OS's making set-up and configuration a large and painful task 2. There was not a facilatator for almost the entire iteration which caused a bottleneck in our ability to fill in requirements and determine if our project design was in scope. | 1. Met with team members and work for about 3-4 hours to resolve all issues with devices and tools. 2. Plan to mitgate absence of facilitaor is to delegate and to swarm on the requirements while several team members develop the skeleton of the appication. | 1. Continue to define Requirements 3. Implement a basic skeleton microservice application | 16
1 | 9/11 -9/22 | 22 | 26 | 18 | 0 - read stack overflow, SQLite documentation, and sqlitetutorial.net pages 1 - colaborated with team members on database design and requirements 2 - worked on updating database design 3 - created SQLite database and table scripts 4 - created python script to test movies.db and its tables 5 - created User stories 6 - verified docker container 7. Prepared presentation and other documentation | 5 | 4 | 3 | 2 | 0.5 | 3 | 0.5 | 8 | 1. Helped to update SPPP 2. Helped to update user stories in both SPPP and pivital tracker. 3. Helped to explore initial database design requirements and needs 4. Updated database design and created SQLite movies.db database 5. Created python test script to verify that the movies.db and tables were created correctly. 6. Created and presented presentation and demo | 1. We had a lot of discussion about database design and how to handel primary keys in order to avoid duplicate records, but we sortted things out. 2. It was tough to try to mange user stories and requirements. Due to the nature of our project we don't have too many user stories, we mostly have development chores. | 1. We resolved database design issues through design implimentaion, failure, design changes, and testing. 2. We asked our facilitator Trevor if it was okay relable some of our user stories as Chores instead. | 1. Load data into database. 2. Put movies.db into docker container 3. Create a microservice for the database contrainer | 26

## James Zheng
Your Lead Roles: Security Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03-09/10 | 12 | 6 | 6 | 0 - how to operate and set up github as well as ssh key 2 - asisted on high level deisgn for the UI and dataset 6- setup github and git as well as all the other programs needed to complete project | 4 | 0 | 2 | 0 | 0 | 0 | 6 | 0 | 1. filled out Meeting 3 of the meeting minutes 2. set up git, github, python, Flask, NodeJs, docker, pivotaltracker | 1. had issue setting up ssh on git 2. Missing facilitator to answer questions and feedbacks to advance with tasks 3. installing docker and getting it setup properly | 1. ssh has been successfully setup 2. we were assigned a facilitator and he was able to answer all of our unanswered questions 3. asking teamates for help and doing our research to resolve the problem | 1. Continue to define Requirements 2. finalize the high level UI design 3. implement a basic skeleton for the program 5. continuing to communicate with team memebrs to complete task on pivotal tracker | 12
2024-01-02 | 9/10-9/24 | 33 | 15 | 18 | 0- refreshing and review of more html/css functions 0- studying and reviewing conan/sonar cube 2- drew out the basic design for the search page 4- test to see if both implemented html file can run and work with each other 5- discussed and settled on a UI layout design | 12 | 0 | 1 | 0 | 4 | 1 | 0 | 0 | 1. started the frontend UI page with html and css coding 2. participated in the presentation and recording of iteration1 3. created user story and task for the team 4. drew out the layout for the search page 5. minutes taker and timekeeper for multiple meeting minutes 6. Assisted on updating the SPPP file with the user stories | 1. being unfamiliar with sonar, conan, and pylint 2. remembering the commands for css and html 3. linking a background picture to the home page | 1. did my research and have a better understanding now 2.looked it up on W3School website for refresher, now I havethe functions that work the way I want it to | 1. finishing the alyout for both home page and search page 2. organizing the html and css codes into Reactjs 3. begin creating some security requirements and implementations | 18

## Rekik Mengstu
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 05/10-05/16 | 6 | 5 | 1 | 0 - learn git and django, read several tutorials 6 - set up git 7 - research | 2 |  |  |  |  | 0.5 | 1 | 0.5 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. not familar with Django framework, hard to write any code on it 2. communication is not clear. Task assignments is not clear. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - continue to learn Django 1 - continue to define requirements 3 - implement a basic hello world on Django | 8
0 | 09/03-09/10 | 2024-10-15 | 7 | 5 | 0 - watched several youtube videos on it 5 - Created User stories 6 - got help from team mates setting up git 7. worked on pivotal track | 3 | 0 | 0 | 0 | 0 | 1 | 5 | 4 | 2. Set-up and configured Git, Podman, Python, Pip, Flask, Github, NodeJs, | 1. different OS's making set-up and configuration complicated 2. There was not a facilatator 3. Being the newest member of the team with the least experience made me doubt myself | 1. Met with team members and work for about 3-4 hours per meeting | 1. Continue to define Requirements 3. Implement a basic skeleton microservice application | 15
1 | 09/11-09/23 | 32 | 22 | 10 | 0. Refreshed on python commands and learned github workflow actions 0. Reachedout for teammates for help 1. Made sure we have all the requirements done for this iteration on pivotal tracker 4. Wrote the Front end software requirement 4. Wrote a Python test script 3. Populated data for the db architecture 5 - Discussed and established a foundational design. 6. Reviewed multiple pull requests | 6 | 2 | 0 | 0 | 16 | 5 | 1 | 0 | 1. Created User story and tasks 2. Created the test script 3. Wrote the Front end requirement 4. Contributed for Database Architecture 5. Worked on Data population with python | 1. Being a total beginner 2. Unfamiliarity with many things in the software world | 1. Teammates being there to help when I am struggling | 1. Continue to reachout 2. Do more research and studying | 30

## Ricky Zheng
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: Configuration Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03 - 09/10 | 18 | 12 | 6 | 0 - learned about git, how to setup multiple technologies (Docker, Python, PIP, nodeJS, SQLite), and learned about Pivotal Tracker. 2- Work together with team developing and brainstorming high level design of project application. 5 - Established and finalized correct channels of team communication. Also, finalized teammeeting dates and times. 6 - Created multiple branches for designated work such as Lab1, adding data sets, adding documention, and updating README.md. Created documentation for team members regarding git commit process. Also, managed pull request as both a assignee, reviewer, and configuration leader. Merged Lab1 pull request and deleted Lab1 branch. | 5 | 0 | 4 | 0 | 0 | 2 | 7 | N/A | 1. Modified and reviewed configuration management section and other sections of SPPP. 2. Set up multiple git branches for different purposes such as Lab1 and adding data sets. Modified README.md in team project repository. 3. Created how-to documentation explaining the process of committing files in Git and GitHub. 4. Wrote 9/5 meeting minutes report. | 1. Initial unfamiliarity with git process when working with other team members. 2. Unfamiliarity working with new tech stack (Docker, Python Flask, etc.) 3. Unsure of final facilitator for our team. 4. Confusion and misunderstanding of necessary documents required for group and individual submission. | 1. Issue has been mostly resolved. Git will be a ongoing learning experience for the team and myself. 2. As development and implementation tasks start to ramp up next week, expect this issue to slowly resolve as the development of the application progresses. 3. Issue resolved. Final facilitator has been assigned to our team. 4. Similiar to issue 2, issue should slowly resolve as team and individual document submission occur this week and the following weeks. | 1 - Continue to learn about project tech stack. 2 - Work on and complete Lab2. 3 - Research and investigate level of effort in implementing Python Flask application with GitHub pipeline. 4 - Manage GitHub project repository. Create, pull request, review, and merge appropriate branches depending on tasks. 5 - Assist and update team members regarding any changes to the team project GitHub repository. | 20
1 - 2 | 09/11 - 09/23 | 30 | 20 | 10 | 0 - Learned about how to implement a basic workflow in GitHub Actions and researched different SCA tools that the pipeline workflow can potentially use later. 2 - Designed initial workflow foundation in GitHub Actions and broke down 3 different jobs to run in workflow. 3 - Implemented GitHub actions workflow in GitHub project repository. There are 3 jobs (Docker-and-Python-Flask-Service, Node-Service, and Docker-and-Node Service) currently set in place for the workflow to run after each commit for all branches. 4 - Tested and ensured all 3 workflow jobs in GitHub actions passed with current design and code. 5 - Discussed and established a foundational design for GitHub Action workflow structure with team members. 6 - Changed documentation folder structure in project repository, created workflows file, created dev branch and multiple feature branches, created and reviewed multiple pull requests. | 4 | 0 | 2 | 14 | 4 | 3 | 3 | N/A | 1. Created GitHub actions workflow file and setup initial workflow pipeline. 2. Created dev branch and multiple feature branches. 3. Modified the documentation structure per iteration for project repository. 4. Wrote and kept track of multiple meeting minutes reports. 5. Modified and created multiple Pivotal Tracker stories. | 1. Unfamiliarity working with DevOps and GitHub Actions. First time creating a workflow YAML file. 2. Unsure of type of pipeline workflow structure to use for our project. 3. Unsure on the type of content specific Pivotal Tracker story types (requirement, investigation, implementation, etc.). | 1. After having implemented the initial foundation of the GitHub actions workflow, I am much more comfortable working with pipeline workflows, at least with the current status of the project. 2. Inital pipeline workflow structure has been made and tested, with all jobs passed. For now, the current workflow structure is working. 3. Discussed Pivotal Tracker concerns with our facilitator, still need some confirmation on story content structure. | 1. The next steps of the pipeline workflow is to implement a functionality that stores Docker containers in some registry. This will require some investigation and changes to the current-workflow.yml file. 2. Research and implement SCA tools that can be potentially implemented with GitHub Actions (SonarQube, CodeQL, etc.). 3. Investigate security concerns and functionality that can be implemented into pipeline workflow. 4. Manage GitHub project repository workflow, testing for any new functionality. | 30

## Alex Flinchum
The sheet shows an example of a student weekly report. Only include the time that you use to work on the project. Each student should make your own sheet to report your work weekly.
Your Lead Roles: QA Leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
0 | 09/03-09/10 | 16 | 10 | 6 | 0 - Learing to set up and exicute the teachnology we will be using 1 - Worked on Database requirments and other documentation 2 - Worked with team in creating our projects focus 5 - Discused team meeting times and channels of communication, alone with the practice of tracking tasks 6 - Assisted team with git and got git setup; Established a new branch and created files for that branch | 4 | 5 | 2 | 0 | 0 | 1 | 4 | N/A | 1. Discussed the QA requirments in the team meetins and reviewd teh details established in the SPPP 2. Set up git on my machine and created the Lab1 from teh main branch along with the team.md file 3. Working on documenting the database requirments in an offical documentation | 1. Having issues with getting pip and flask installed 2. Need to advance my knowledge of working with docker and running it 3. Confusion on the location of documentation and how to go about implimenting it | 1. Will set about time to go ver pip and flask instilation as well as knowledge on docker, This can be during a team meeting where we set asside time to run through these areas 2. Issue Resolved: the location of our teams documentation has been established and have been able to run through it | 1. Continue to learn the procjects tech, specifically docker and flask 2. Complete database requirment documentation 3. Research pipline cpabilities for a python project | 20
2024-01-02 | 09/11 - 09/23 | 28 | 18 | 10 | 0 - Finished geting up to speed with docker/Python tools 1 - Designed diagram of database flow and storage. 2 - Created the database requirments. 3 - Started working on frontedn development and getting knowledge on the process 4 - Created and tested test cases for manual testing 5 - Discussed and established the database design with team members. 6 - Finished installing python tools. | 1 | 4 | 8 | 2 | 7 | 3 | 3 | N/A | 1. Created a UML Diagram of the project database design that used to focus the concept and implement upon. 2. Wrote test cases for two MVP user stories that will be used to create future test cases in teh future of this project. 3. Executed said test cases. 4. Added to the projects documentation explaing said test cases and teh mention database design. | 1. Had issues understanding the process of using docker and building/running the project 2. Taking time to familarize myself with react development to work on the frontend. | 1. Issue Resolved: Was able to gane an understanding of docker and building/running the project from other team members. 2. Will focus my time on ramping up my work on the frotend of development. | 1. Continue to work on the testing process of the project, leading the plans that will be needed in this area 2. Dedicate time to working on Frontend devlopment tasks. 3. Help with any database design issues that come up. | 30