## Sheet1
This sheet provides some common risks in student projects. You should check if it applies to your group project. You should also feel free to add other risks. Exemplary analysis is also added.
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
personel | add new team members | One or more new team members. | 5 | 1 | 1 | 5 | team leader and all members | 2024-09-11 | Spend extra time to bring up to speed | Team member has been brought up to speed | retired
Communication | duplicate work | One or more teammates not understanding the scope of what they need to work on | 3 | 2 | 4 | 48 | team leader and all members | 2024-10-07 | Clearly communicate who is working on what This will be something we need to constantly address | Keep communicating, rely more on the board | open
| worked on wrong components | One or more teammates not understanding the scope of their work | 5 | 2 | 3 | 12 | team leader and all members | 2024-10-07 | Clearly define what needs to be worked on This is an issue that will constantly need to be address and proablly never retired. | Keep communicating, rely more on the board | open
| useless work | Team members not communication or understanding the scope of their work. | 4 | 3 | 4 | 24 | team leader and all members | 2024-10-07 | Clearly define what needs to be worked on | Check in on team mates, and ask questions | open
| inconsistent work | Everyones code is styled diiferently which causes confusion and unneed complexity | 3 | 2 | 2 | 24 | team leader and all members | 2024-10-07 | Establish codeing standards | Keep communicating, Rely more on the board Review code in PR more closely | open
Requirements | unclear requirements | One or more teammates are not familar with writing requirements | 4 | 2 | 3 | 24 | Liz and Rekik | 2024-09-12 | Have the requirement SME lead the task and teach the team how to write clear requirements or clear any unclear requirements up | Review the requirements as a team and build unit test based on requirements | retired
| scope creep | One feature may grow in scope | 3 | 2 | 5 | 60 | Liz and Rekik | 2024-10-07 | Check in on team members and watch tasks on the board | Swarmed on requirements task that had scope creep | open
| constant requirements changes | What the application should be doing is constantly changing | 1 | 1 | 2 | 50 | Liz and Rekik | 2024-09-12 | Ensure implementation matches requirements to reduce overhead | No requirment changes so far | retired
Management | improper task assignments | People are being assgined work they are not ready to under take | 2 | 1 | 2 | 40 | team leader and all members | 2024-09-18 | Check in and determine how task are going and reassign as required | Task have so far been in scope | retired
| improper planning | Scope of work is not undnerstood and deadlines are missed | 2 | 1 | 2 | 40 | team leader and all members | 2024-09-18 | As a team review the plan and determine if it still makes sense | Plan is on schedule | retired
| lack of management skills | One or more teammates do not have experence mangaging a team. | 1 | 1 | 1 | 25 | team leader and all members | 2024-09-24 | Pair members up to learn from member that do have XP | Too early to tell | retired
Technology competence | Not familiar with the framework used | Only one person has framework xp | 5 | 1 | 5 | 25 | Josh | 2024-09-26 | Build small app and demo then have team learn | Too early to tell | open
| Not familiar with the programming language used | One or more teammates are not familar with programming | 4 | 2 | 5 | 40 | Josh/Ricky | 2024-09-24 | Build small app and demo then have team learn | Too early to tell | retired
| Not familiar with unit testing | One or more teammates are not familar with unit testing | 2 | 3 | 5 | 60 | Josh/Ricky/James? | 2024-09-30 | Build small app and demo then have team learn | Too early to tell | open
| Other technology incompetence | One or more teammates are not familar with Docker | 2 | 2 | 5 | 80 | Josh | 2024-09-30 | Build small app and demo then have team learn | Too early to tell | open
| Not familiar with Git | One or more teammates are not familar with git | 3 | 3 | 4 | 36 | Josh/Alex/Ricky | 2024-09-24 | Use lab as learning experence | Team mates are pairing up and helping each other. There are issue but it seem that we hare handling them as a team. | retired
Design and implementation | Improper design | Design does not work | 1 | 1 | 1 | 25 | Josh/Liz | 2024-09-18 | Develop design based on industry XP and known design | Design seem on point so far | retired
| improper technology stack | Wrong tools to execute design | 2 | 1 | 5 | 100 | Josh | 2024-09-18 | Use known tech and easy to learn tech for new Devs | Tech stack had minor addition of docker compose after Tuesdays Lecture | open
| Messy code | Teammates not following coding standards or branch guidlines | 3 | 1 | 2 | 30 | Josh/Ricky/Alex | 2024-10-07 | Adhere to coding guidelkine pep 8 This is something that is going to have to be a constant risk that we attempt to mitigate. | Too early to tell | open
Testing | Not enough testing | Lack of quality code | 3 | 2 | 2 | 24 | Alex/Ricky | 2024-09-26 | Ensure testing is integrated into the pipeline to maintain high quality of code. | Too early to tell | open
Integration and deployment | Not enough time for integration and deployment | Issues preventing the deployment of software | 3 | 2 | 5 | 60 | team leader and all members | 2024-09-26 | Start building pipeline as soon as possible. | Too early to tell | retired